## Slide 1
Project Performance Measurement Approach
In
Road Construction Industry
Using EVPM
Pedram Daneshmand; pedramd@bluevisions.com.au
Adel Khreich; adelk@bluevisions.com.au
Australia

## Slide 2: Introduction
Project Monitoring & Control
  Ideal Control System
  Main Elements: Cost, Time, Quality and Safety
  Techniques:
    Leading parameter
    Activity based ratios
    Variances
    Earned Value Performance Measurement (EVPM)

## Slide 3: Ideal Control System
Example: Construction of a bridge
  Budget: $10’000’000
  Project Duration: 1 year
  After 6 months, we have received an invoice of $5’000’000. The question is how much job really done?
  More accurate answer, ideal Control System

## Slide 4: EVPM Background
Industrial base – at the turn of the 20th century
US - Department of Defence
  Idea took root in 1960’s
  C/SCSC (35 criterions) in 1967
  Emerged as a PM tool in the early 1990’s

## Slide 5: EVPM Process
Decompose the WBS
Assign responsibility
Planning/Scheduling
Develop time-phased budget
Objective measures of performance
Set the performance baseline
Monitor & Report

## Slide 6: Case Study – NWT-Way, Sydney, Australia
Bus rapid transit line
A$500M D&C
Feb 04 to Dec 07
24 Km
30 Stations
7 Bridges
1 Underpass
Cycleway, pedestrian facilities

## Slide 7: Case Study – NWT-Way, Sydney, Australia

## Slide 8: Case Study – NWT-Way, Sydney, Australia

## Slide 9: 1 – WBS & Work Packages
North West
T-Way
Zone 1
Zone 2
Zone 3
Zone 4
Section 1
Section 2
Section 3
Section 4
Section 5
Section 6
Section 7
Section 8
50
Locations
(all Sections)
34
Disciplines
L1
L2
L3
L4
L5

## Slide 10: 2 – Budget Cost Allocation
Locate the 4th or 5th level of WBS.
Get the direct cost info.
Allocate costs over each Work Package.
Allocate the linear relationship or a more accurate non-linear expenditure against time.

## Slide 11: 3 – Schedule & Plan Value (PV)
Prepare your schedule plan using CPM
Locate the WP’s within the schedule
Allocate the costs to WP’s
Create the S-Curve, PV or BCWS
Do resource levelling
Check the financing plan
Finalise the PV curve

## Slide 12: Plan Value (PV)

## Slide 13: 4 – Progress Monitoring/Updating
Schedule updating Fortnightly with:
  Actual Start & Finish dates
  Revised Start & Finish dates
  Revised Duration
  Updated Incomplete activities
    0-100; 50-50; 25-75; and 33-67
    Level of Effort (LOE)
    Percent Complete

## Slide 14: 4 – Progress Monitoring/Updating
Cost updating Monthly with:
  Claim Costs
  Site Actual Costs (AC) or ACWP

## Slide 15: 5 – EVPM calculation
EV(BCWP) = % Comp x PV(BCWS)
Schedule Variance (SV) = EV – PV
Cost Variance (CV) = EV – AC
SPI = EV / PV
CPI = EV / AC
PCP = PV / Total Budget
PCA = EV / Total Budget
EAC = AC + ETC

## Slide 16: 6 – Data Analysis & Progress Report
Summary Programme Progress Report
Critical Path Investigation
Design Progress Report
Construction Progress Report
Earned Value Progress Report
Schedule/Cost Variance Progress Report
Cash Flow Report

## Slide 17: 6a – Programme Progress Report
Cumulative Progress
Monthly Progress
Description
Planned
Actual*
Variance
Planned
Actual*
Variance
Zone 1:
Design Status (%) =
100%
100%
0%
0.0%
0.0%
0.0%
Construction Status (%) =
100%
100%
0%
0.0%
0.0%
0.0%
Zone 2:
Design Status (%) =
100%
100%
0%
0.0%
0.0%
0.0%
Construction Status (%) =
100%
100%
0%
0.0%
0.0%
0.0%
Zone 3:
Design Status (%) =
100%
100%
0%
0.0%
0.0%
0%
Construction Status (%) =
77.4%
86.9%
9.5%
3.9%
3.5%
0.4%
Zone 4:
Design Status (%) =
100%
100%
0%
0.0%
0.0%
0.0%
Construction Status (%) =
67.2%
70.1%
2.9%
9.3%
7.1%
2.2%
TOTAL:
Design Status (%) =
100%
100%
0%
0.0%
0.0%
0.0%
Construction Status (%) =
85.7%
88.7%
3.0%
3.5%
2.8%
0.7%
TOTAL Project Status (%) =
86.8%
89.5%
2.7%
3.1%
2.6%
0.5%

## Slide 18: 6b – Critical Path Investigation

## Slide 19: 6c – Design Progress Report

## Slide 20: 6d – Construction Progress Report

## Slide 21: 6e – Earned Value Progress Report

## Slide 22: 6f – S/C Variance Progress Report

## Slide 23: 6g – Cash Flow Report

## Slide 24: Conclusion
EVPM is a good tool for improving the analysis of progress and performance on a construction project.
Although level 4th WP’s give accurate results, site engineers feel more confident at 5th level.
General overheads and profits should be eliminated from the analysis so that actual expenditure can be directly compared with budgeted expenditure.
Within this closed network, activities are updated with time data and WP’s updated with cost info.
The test data needs to be expanded with data from a wider range of road projects to provide more practical usages and procedures of EVPM system.
Getting the accurate cost figures from financial dept and the real time and performance data from site engineers, makes the EVPM system a reliable performance measurement tool.

## Slide 25: Acknowledgment
Consulting services was undertaken and fully supported by:
  Blue Visions Management Pty Ltd (BVM), Sydney, Australia.
Database support has been provided by:
  Leighton Contractors Pty Ltd (LCPL), Australia.

## Slide 26: THANK YOU